## Product-Backlog
id | theme | as a/an | I want to… | so that… | notes | acceptance criteria | added in sprint | Priority | story points | Done?
19 | Shape Family | Developer | Implement an abstract base class shape() | Facilitate inheritance to instantiate shape classes | virtual methods: draw() , move() , perimeter() , area() |  |  | 1
20 | Shape Family | Developer | Implement shape classes derived from base shape(): line, polyline, polygon, rectangle, ellipse | The program has shapes to draw for the user | properties: dimensions, pen color, pen width, pen style, pen cap style, pen join style, brush color, brush style |  |  | 1
21 | Shape Family | Developer | Implement a shape class derived from base shape(): text | The program has drawable text the user can utilize | properties: alignment, point-size, font family, font style, font weight |  |  | 1
22 | Shape Family | Developer | Overload the equality and less-than operators for id comparision | facilitate sorting of shapes by id |  |  |  | 2
23 | Shape Family | Developer | Disable copy operations for all shape types by marking copy constructor/assignment operator as deleted |  |  |  |  | 2
24 | Vector Class | Developer | Convert the provided double vector example into a templated class | We have a vector capable of handling any type, but more specifically our new shape family of classes and user class | need: default constructor, constructors for one or more arguments, copy constructors, copy assignments, move constructor, move assignment, destructor, basic iterator member type with begin() and end() methods. |  |  | 2
4 | Functionality | User | Have all changes save from session to session | Work done is saved |  | - User is able to save and overwrite files - User is able to see the save location - Admin is able to save and overwrite files - Admin is able to see the save location - Admin is able to see the save log - All task, test conditions satisfied |  | 3 | 15
5 | Functionality | User | Have objects represented on a display plane with the following: minimum 1000 x 500 pixels (horizontalxVertical);top left of plane is origin (0,0), bottom right will be (1000,500) | Sufficient area to work with displayed shapes |  | User is able to position shapes where if it were to be half way off the canvas, it will only display/render the side that is on the canvas. |  | 3 | 5
8 | Functionality | User | Generate a list of shapes which have an area, sorted by area |  |  | User is able to view a list of shapes with an area and sort them based on area, either in ascending order or descending order. |  | 3 | 10
9 | Functionality | User | Generate a list of shapes which have a perimeter, sorted by perimeter |  |  | User is able to view a list of shapes with a perimeter and sort them based on perimeter, either in ascending order or descending order. |  | 3 | 5
10 | Functionality | User | Generate a list of shapes sorted by id, with all properties presented |  |  | User can view the database of shapes, but cannot add, remove, edit or move any shapes. |  | 3 | 5
6 | Functionality | User | Have an initial database of shapes read in from a file at the start of the program | I have initial shapes to work with |  | - User is able to login as a guest and view the program without full functionality. - Administrator is able to add/ remove, change color/ line size, and move/ rotate a shape object. - All changes are saved to an internal .txt file and read to the main program during compilation. - All task, test conditions satisfied |  | 4 | 15
7 | Functionality | Administrator | Have an initial database of users read in from a file | I am able to login with the proper credentials |  | - Admin is able to login using their username(login) and password. - Admin is able to view the entirety of user(admins included) data base. |  | 4 | 20
11 | Functionality | Administrator | Be able to change shape attributes |  |  | - User is able to login as a guest and view existing shapes without ability to edit them. - Administrator is able to change color/ line size of a shape object. - All changes are saved to an internal .txt file and read to the main program during compilation and displayed immediately. - All task, test conditions satisfied |  | 4 | 6
12 | Functionality | Administrator | Be able to add/remove shapes |  |  | - User is able to login as a guest and view existing shapes without ability to edit them. - Administrator is able to add a new shape object and view it successfully. - Administrator can remove existing shapes. - All changes are saved to an internal .txt file and read to the main program during compilation and displayed immediately. - All task, test conditions satisfied |  | 4 | 6
13 | Functionality | Administrator | Be able to move objects |  |  | - User is able to login as a guest and view existing shapes without ability to edit them. - Administrator is able to change orientation and position of a shape object. - All changes are saved to an internal .txt file and read to the main program during compilation and displayed immediately. - All task, test conditions satisfied |  | 4 | 6
15 | Interface | Administrator | Be able to login, to gain my administrator privledges | Critical functions are protected from anonymous manipulation |  | - User is able to login as an admin to add/ remove, change color/ line size, and move/ rotate a shape object. - User is able to login as an admin to add/ remove or edit account information.All task, test conditions satisfied |  | 4 | 6
16 | Interface | User | By default, be a guest user with limited permissions at startup |  |  | The user is automatically treated as a guest account, and has access only to the information readily available to them; they are not capable of modifying existing shapes. |  | 4 | 6
1 | Administrative | Deliverer | Provide logistics/maintenance plan with pricing | Customer is aware of future costs upfront |  |  |  | 5
2 | Administrative | Deliverer | Provide list of supported environments | Customer known where the software can be deployed |  |  |  | 5
3 | Administrative | Deliverer | Provide sales pitch | Customer is aware of the benefits of purchasing the software |  |  |  | 5
14 | Interface | User | Be able to view contact information of the developer | I may contact the developer in the case of technical issues, or help required that is outside the scope of the built in help functionality |  | The user can access the provided contact information. |  | 5 | 5
17 | Interface | User | Be able to access a help feature | can see how the program is properly utilized, and what features are available to me |  | - Both users and admins can successfully call the help feature of the program. - They can view the text files and descriptions of every feature of the program. - They can navigate different sections of the help manual. |  | 5 | 5
18 | Interface | User |  | I can suggest potential changes to the program in future versions |  | All users can submit feedback. |  | 5 | 5
25 | Project Requirements | Student | Be able to submit testimonial | To document our program |  |  |  | 5
26 | Project Requirements | Student | Submit UML diaram | To document our class hierachy |  |  |  | 5

## SprintOne-Backlog
id | Description | Tasks | Tests | Specifics | Esimation | Sprint Priortity | Assignee
19 | Shape Family | Implement an abstract base class shape() | Facilitate inheritance to instantiate shape classes | virtual methods: draw() , move() , perimeter() , area() | 2 | 1 |  | include QT painter pointer HA!
20 | Shape Family | Implement shape classes derived from base shape(): line, polyline, polygon, rectangle, ellipse | The program has shapes to draw for the user | properties: dimensions, pen color, pen width, pen style, pen cap style, pen join style, brush color, brush style | 2 | 1
21 | Shape Family | Implement a shape class derived from base shape(): text | The program has drawable text the user can utilize | properties: alignment, point-size, font family, font style, font weight | 5 | 1 |  | suggestion: implement this after the 1st sprint if we run out of time - YD
22 | Shape Family | Overload the equality and less-than operators for id comparision | facilitate sorting of shapes by id |  | 2 | 2
23 | Shape Family | Disable copy operations for all shape types by marking copy constructor/assignment operator as deleted |  |  | 2 | 2
24 | Vector Class | Convert the provided double vector example into a templated class | We have a vector capable of handling any type, but more specifically our new shape family of classes and user class | need: default constructor, constructors for one or more arguments, copy constructors, copy assignments, move constructor, move assignment, destructor, basic iterator member type with begin() and end() methods. | 3 | 2 | Michael has implemented/tested it
15 | Interface | Administrator | Be able to login, to gain my administrator privledges | Critical functions are protected from anonymous manipulation | 4 | 6 | Connor has finished elements of this assignment: login, pass | - User is able to login as an admin to add/ remove, change color/ line size, and move/ rotate a shape object. - User is able to login as an admin to add/ remove or edit account information.All task, test conditions satisfied

## Charts
Release Burndown
Only edit shaded columns, others are calculated
Sprint | Story points |  |  | Percent Complete | Min | Max
| Remaining | Done | Variation
0 | 190 | 0 | 0 | 0% | 0 | 190
1 | 180 | 50 | 0 | 22% | 0 | 180
2 | 180 | 130 | 80 | 42% | -80 | 100
3 | 90 | 220 | 80 | 71% | -80 | 10
4
5
6
7
8
9
10

## Lists
0
5
10
20
30
50
80
130
200
400
1000

## Copy of Product-Backlog
id | theme | as a/an | I want to… | so that… | notes | acceptance criteria | added in sprint | story points
| Administrative | Deliverer | Provide logistics/maintenance plan with pricing | Customer is aware of future costs upfront
| Administrative | Deliverer | Provide list of supported environments | Customer known where the software can be deployed
| Administrative | Deliverer | Provide sales pitch | Customer is aware of the benefits of purchasing the software
| Functionality | User | Have all changes save from session to session | Work done is saved
| Functionality | User | Have objects represented on a display plane with the following: minimum 1000 x 500 pixels (horizontalxVertical);top left of plane is origin (0,0), bottom right will be (1000,500) | Sufficient area to work with displayed shapes
| Functionality | User | Have an initial database of shapes read in from a file at the start of the program | I have initial shapes to work with
| Functionality | Administrator | Have an initial database of users read in from a file | I am able to login with the proper credentials
| Functionality | User | Generate a list of shapes which have an area, sorted by area
| Functionality | User | Generate a list of shapes which have a perimeter, sorted by perimeter
| Functionality | User | Generate a list of shapes sorted by id, with all properties presented
| Functionality | Administrator | Be able to change shape attributes
| Functionality | Administrator | Be able to add/remove shapes
| Functionality | Administrator | Be able to move objects
| Interface | User | Be able to view contact information of the developer | I may contact the developer in the case of technical issues, or help required that is outside the scope of the built in help functionality
| Interface | Administrator | Be able to login, to gain my administrator privledges | Critical functions are protected from anonymous manipulation
| Interface | User | By default, be a guest user with limited permissions at startup
| Interface | User | Be able to access a help feature | can see how the program is properly utilized, and what features are available to me
| Interface | User | Be able to submit testimonial | I can suggest potential changes to the program in future versions
| Shape Family | Developer | Implement an abstract base class shape() | Facilitate inheritance to instantiate shape classes | virtual methods: draw() , move() , perimeter() , area()
| Shape Family | Developer | Implement shape classes derived from base shape(): line, polyline, polygon, rectangle, ellipse | The program has shapes to draw for the user | properties: dimensions, pen color, pen width, pen style, pen cap style, pen join style, brush color, brush style
| Shape Family | Developer | Implement a shape class derived from base shape(): text | The program has drawable text the user can utilize | properties: alignment, point-size, font family, font style, font weight
| Shape Family | Developer | Overload the equality and less-than operators for id comparision | facilitate sorting of shapes by id
| Shape Family | Developer | Disable copy operations for all shape types by marking copy constructor/assignment operator as deleted
| Vector Class | Developer | Convert the provided double vector example into a templated class | We have a vector capable of handling any type, but more specifically our new shape family of classes | need: default constructor, constructors for one or more arguments, copy constructors, copy assignments, move constructor, move assignment, destructor, basic iterator member type with begin() and end() methods.
| Project Requirements | Student | Run Doxygen | To document our program
| Project Requirements | Student | Submit UML diaram | To document our class hierachy
Project Requirements
Project Requirements