## Sheet1
id | Description | Tasks | Tests | Specifics | Esimation | Sprint Priortity | Assignee | Deliverables
19 | Shape Family | Implement an abstract base class shape() | Facilitate inheritance to instantiate shape classes | virtual methods: draw() , move() , perimeter() , area() | 2 | 1 | Michael | include QT painter pointer HA!
20 | Shape Family | Implement shape classes derived from base shape(): line, polyline, polygon, rectangle, ellipse | The program has shapes to draw for the user | properties: dimensions, pen color, pen width, pen style, pen cap style, pen join style, brush color, brush style | 10 | 1 | Michael | Shapes are implemented and can be further worked withe
21 | Shape Family | Implement a shape class derived from base shape(): text | The program has drawable text the user can utilize | properties: alignment, point-size, font family, font style, font weight | 5 | 1 | Michael | suggestion: implement this after the 1st sprint if we run out of time - YD
22 | Shape Family | Overload the equality and less-than operators for id comparision | Allows ID comparisons between shapes | can compare ID properties of different objects | 1 | 2 | Yuliy | Discovered that Qt does this automatically
24 | Vector Class | Convert the provided double vector example into a templated class | We have a vector capable of handling any type, but more specifically our new shape family of classes and user class | need: default constructor, constructors for one or more arguments, copy constructors, copy assignments, move constructor, move assignment, destructor, basic iterator member type with begin() and end() methods. | 3 | 2 | Michael has implemented/tested it | The vector class performs all expected tasks
15 | Interface | Administrator | Be able to login, to gain my administrator privledges | Critical functions are protected from anonymous manipulation | 4 | 6 | Connor has finished elements of this assignment: login, pass | - User is able to login as an admin to add/ remove, change color/ line size, and move/ rotate a shape object. - User is able to login as an admin to add/ remove or edit account information.All task, test conditions satisfied
16 | Interface | User | By default, be a guest user with limited permissions at startup | Windows are hidden from non-Admin users | 4 | 6 | Michael | The user is automatically treated as a guest account, and has access only to the information readily available to them; they are not capable of modifying existing shapes.
14 | Interface | User | Be able to view contact information of the developer | I may contact the developer in the case of technical issues, or help required that is outside the scope of the built in help functionality | 5 | 5 | Connor | The user can access the provided contact information.
17 | Interface | User | Be able to access a help feature | can see how the program is properly utilized, and what features are available to me | 5 | 5 | Yuliy/Connor | - Both users and admins can successfully call the help feature of the program. - They can view the text files and descriptions of every feature of the program. - They can navigate different sections of the help manual.
18 | Interface | User | Have a feedback feature | I can suggest potential changes to the program in future versions | 5 | 5 | Yuliy/Michael | All users can submit feedback.
30 | Interface | User | Save feedback | Save and read from the feedback file | 3 | 5 | Yuliy | Feedback saves from session to session