## Sheet1
id | Description | Tasks | Tests | Specifics | Esimation | Sprint Priortity | Assignee | Deliverables
19 | Shape Family | Implement an abstract base class shape() | Facilitate inheritance to instantiate shape classes | virtual methods: draw() , move() , perimeter() , area() | 2 | 1 | Michael | include QT painter pointer HA!
4 | Functionality | User | Have all changes save from session to session | Work done is saved | 5 | 3 | Yuliy | - User is able to save and overwrite files - User is able to see the save location - Admin is able to save and overwrite files - Admin is able to see the save location - Admin is able to see the save log - All task, test conditions satisfied
5 | Functionality | User | Have objects represented on a display plane with the following: minimum 1000 x 500 pixels (horizontalxVertical);top left of plane is origin (0,0), bottom right will be (1000,500) | Sufficient area to work with displayed shapes | 5 | 3 | Michael | User is able to position shapes where if it were to be half way off the canvas, it will only display/render the side that is on the canvas.
8 | Functionality | User | Generate a list of shapes which have an area, sorted by area | Shapes can be sorted by area | 10 | 3 | Michael | User is able to view a list of shapes with an area and sort them based on area, either in ascending order or descending order.
9 | Functionality | User | Generate a list of shapes which have a perimeter, sorted by perimeter | Shapes can be sorted by perimeter | 5 | 3 | Michael | User is able to view a list of shapes with a perimeter and sort them based on perimeter, either in ascending order or descending order.
10 | Functionality | User | Generate a list of shapes sorted by id, with all properties presented | Shapes can be sorted by id | 5 | 3 | Michael | User can view the database of shapes, but cannot add, remove, edit or move any shapes.
6 | Functionality | User | Have an initial database of shapes read in from a file at the start of the program | I have initial shapes to work with | 15 | 4 | Yuliy | - User is able to login as a guest and view the program without full functionality. - Administrator is able to add/ remove, change color/ line size, and move/ rotate a shape object. - All changes are saved to an internal .txt file and read to the main program during compilation. - All task, test conditions satisfied
7 | Functionality | Administrator | Have an initial database of users read in from a file | I am able to login with the proper credentials | 2 | 4 | Michael | - Admin is able to login using their username(login) and password. - Admin is able to view the entirety of user(admins included) data base.
30 | Functionality | User/Admin | Design a parser that would read from a file shapes.txt into a vector of shapes (creating 1 shape at a time | Parser works on multiple runs | 30 | 2 |  | A parser reads from the text file, triggers a mini-parser based on the shape type, reads in the information from it and creates and object that then gets stored inside a vector of shapes until all fhapes from shapes.txt are read in
11 | Functionality | Administrator | Be able to change shape attributes | Be able to adjust all shape attributes | 6 | 4 | Michael | - User is able to login as a guest and view existing shapes without ability to edit them. - Administrator is able to change color/ line size of a shape object. - All changes are saved to an internal .txt file and read to the main program during compilation and displayed immediately. - All task, test conditions satisfied
13 | Functionality | Administrator | Be able to move objects | Be able to adjust shape coordinates | 6 | 4 | MIchael | - User is able to login as a guest and view existing shapes without ability to edit them. - Administrator is able to change orientation and position of a shape object. - All changes are saved to an internal .txt file and read to the main program during compilation and displayed immediately. - All task, test conditions satisfied
1 | Administrative | Deliverer | Provide logistics/maintenance plan with pricing | Customer is aware of future costs upfront | 2 | 5 | Roman | Have a specific breakdown of pricing and billing
2 | Administrative | Deliverer | Provide list of supported environments | Customer known where the software can be deployed | 2 | 5 | Yuliy | Provide a list of environments supported by the program
3 | Administrative | Deliverer | Provide sales pitch | Customer is aware of the benefits of purchasing the software | 2 | 5 | Connor | Sales pitch
3 | Administrative | Deliverer | Provide UML diagrams | Provides UML Diagrams | 2 | 5 | Connor/Roman | Have diagrams that explain the flow of the program
3 | Administrative | Deliverer | DOxygen | Generates comments for the code | 2 | 5 | Roman | DOxygen documentation in the HTML/XML formats